## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Setup Java Project and Database Connection | MUST HAVE | MySQL | Hariprasath B | Completed
S1 | S1 | US-002 | Create Transaction Model Class | MUST HAVE | No Dependency | Hariprasath B | Completed
S1 | S1 | US-003 | Implement DAO Pattern (TransactionDAO) | MUST HAVE | JDBC | Hariprasath B | Completed
S2 | S2 | US-004 | Implement Fraud Detection Rules | MUST HAVE | Transaction Model | Hariprasath B | Completed
S2 | S2 | US-005 | Risk Score Calculation Logic | MUST HAVE | Fraud Rules | Hariprasath B | Completed
S2 | S2 | US-006 | Store Fraud Result in Database | SHOULD HAVE | DAO | Hariprasath B | Completed
S3 | S3 | US-007 | Transaction Generator Implementation | MUST HAVE | Model | Hariprasath B | Completed
S3 | S3 | US-008 | Testing Fraud Scenarios | MUST HAVE | Fraud Logic | Hariprasath B | In Progress
S3 | S3 | US-009 | GitHub Setup & Documentation | SHOULD HAVE | Git | Hariprasath B | In Progress
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 55 | 17 | 9 | 7 | 6 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Project Introduction & Requirement Analysis | 2026-02-04 | 2026-02-05 | Hariprasath B | Planning | 3-Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Create Java Project & Setup Environment | 2026-02-05 | 2026-02-06 | Hariprasath B | Setup | 3-Completed | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | MySQL Database Creation | 2026-02-06 | 2026-02-07 | Hariprasath B | Database | 3-Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Create Tables (Users, Transactions, Fraud_Log, Risk_Score) | 2026-02-08 | 2026-02-09 | Hariprasath B | Database | 3-Completed | 6 | 2 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | Develop Transaction Input Module | 2026-02-09 | 2026-02-10 | Hariprasath B | Coding | 3-Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | Implement Input Validation Logic | 2026-02-10 | 2026-02-10 | Hariprasath B Vetrivel R | Coding | 3-Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | Implement Fraud Detection Rules | 2026-02-11 | 2026-02-12 | Hariprasath B Vetrivel R | Coding | 3-Completed | 8 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 8 | Risk Score Calculation Logic | 2026-02-12 | 2026-02-13 | Hariprasath B Vetrivel R | Coding | 3-Completed | 6 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 9 | Alert Generation & Logging | 2026-02-14 | 2026-02-15 | Hariprasath B Vetrivel R | Build | 2- In Progress | 5 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 10 | System Testing & Debugging | 2026-02-16 | 2026-02-17 | Hariprasath B Vetrivel R | Testing | 2- In Progress | 8 | 3 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | Difficulty in setting up Java project environment | Installed required tools and configured Java and IDE properly
Sprint 1 | Day 5 | Confusion in designing database tables | Reviewed project requirements and finalized database schema
Sprint 2 | Day 8 | Issue in connecting Java with MySQL database | Used JDBC connector and tested database connectivity
Sprint 2 | Day 10 | Error in implementing fraud detection rules | Debugged code and corrected rule logic
Sprint 3 | Day 14 | Incorrect risk score calculation | Fixed formula and validated with sample transactions
Sprint 3 | Day 16 | Fraud alerts not storing in database | Checked SQL queries and corrected insert statements
Sprint 4 | Day 20 | Simulation engine generating incorrect data | Modified random transaction generation logic
Sprint 5 | Day 23 | Difficulty in integrating all modules | Performed integration testing and resolved errors

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Start Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-04 | 2026-02-11 | Hariprasath B, Vetrivel R | Reviewing project requirements and designing database structure | Assuming database schema without proper planning | Developing transaction input and validation modules | Successfully created MySQL database, tables, and completed transaction input module
2 | Sprint 2 | 2026-02-12 | 2026-02-17 | Hariprasath B, Vetrivel R | Implementing fraud detection rules and risk score calculation | Ignoring error handling during fraud detection implementation | Testing fraud detection system and improving accuracy | Completed fraud detection engine, risk score module, and generated fraud alerts